# [Section 5] Terms of Reference (ToR)

Terms of Reference for Design and Author Supervision

WHEREAS the Employer requires that certain works should be executed: The Design and Author Supervision Services for the Construction of IT Training Center for the project titled “The Capacity Building of National Informatization for Digital Transformation in the Kyrgyz Republic” in Bishkek, Kyrgyz Republic and has accepted a Bid by the Consultant for the execution and completion of such Services.

Article 1.  Definitions

1.1 Addendum:  A supplement to the bidding documents.

Article 2.  Description of Design Work

2.1 The work comprises all of the followings and all deliverables under this contract must be submitted in English and Russian. Bilingual format (English and Russian) may be used if needed:

2.1.1. Design and Construction Document Services (including Preliminary Survey & options, SD, DD, CD, and tender document)

- Site Investigation and Required surveys (Including Existing facilities within the project site, Geographical, Topographical, Structural(if any), and preliminary site layout options at the basis of land use plan)

- Preparation of design and other engineering services necessary to bring the work to the construction readiness state for the projects mentioned in the Agreement.

- Preparation of all the developed construction documents including the Drawings, Technical Specifications, Bill of Quantities, and Cost Estimate for the construction works including civil engineering works, Structural works, Architectural, Interior, Plumbing, Sanitary, Mechanical, Electrical, HVAC, information and communication, firefighting works, soil investigation reports, structural calculation report and other necessary interior and exterior works in accordance with the furnished design criteria.

- Design should include (or specify in the drawing) the below:

- All the connection works of the utility lines to the project site.

- Boundary wall, Main gate, Landscaping and Pavement works (if required)

- Interior design for key rooms and finalization of specifications for general furniture and fixtures, to be included in the construction scope for bidding purposes.

- Interior finish and built-in furniture according to the consultation with the Employer (KOICA CM, PMC, etc.)

- The undertakings by others (e.g. Recipient country undertakings, etc.) in the design drawings and related documents according to the consultation with the Employer (KOICA CM, PMC, etc.)

2.1.2. The assignment consist of the services for the construction works of the project mentioned below:

-Project purpose: New Construction of ICT Education Center

-Project plot location: Ch.Aitmatov Avenue, 104v, Bishkek

-Project plot Area: 1.0 ha

-Gross Floor Area 1,179 M2 (±5%) of two(2) story building.

-Construction budget limit is USD 1,704,050 (including a stand-by generator)

※ The total gross floor area is subject to change within ±5% range

※ See the attached [Section 6] Reference Material for further details and information.

2.2. Design Criteria

2.2.1. General Considerations

A.  Space Program

※ See the attached [Section 6] Reference Material for the requested space program.

B.  Design phases and timeline

(a) Design should be developed as below phases:

-Preliminary design:  Survey results, three (3) alternative options (each option includes land use plan (if necessary), building layout & access, floor plans, construction work scope by undertaking parties, etc.)

- Schematic design (SD) : basic design developed from the selected layout option.

-Design development (DD) : detailed design developed from the approved SD.

-Construction document (CD): final detailed design document package for construction execution that was approved from both local authorities and the Employer.

(b) The Consultant should establish appropriate Design Timeline and submit it to the Employer for review and approval.

(c) The Design Timeline should include: every design phases (Preliminary, SD, DD, CD), the Employer’s review period, and Local state’s Permit including Urban planning permit, Design permit, Building permit, other required deliberations & assessment prior to the Construction bidding announcement.

C.  Design submittal list for each phase

(a) Submittal List for the Schematic Design (SD) Phase

| Submittal | Contents | Copy | Note |
| --- | --- | --- | --- |
| Schematic Design(SD) Documents | Implementation Plan for Design works | 2 | Hard & soft copy |
|  | Design Schedule (including Drawings, Design Calculation Report, Priced BOQ and Unpriced BOQ, Specifications, etc.) | 2 | Hard copy with A1 or A2 & soft copy |
|  | Design Organization Chart etc. |  |  |
|  | Schematic Design Drawings and Documents |  |  |
|  | All documents should be submitted as hard and soft copy. Soft copy can be delivered via USB and e-mail. All deliverables under this contract must be submitted in English and Russian versions. Bilingual format (English and Russian) may be used if needed. |  |  |

(b) Submittal List for the Design Development (DD) Phase

| Submittal | Contents | Copy | Note |
| --- | --- | --- | --- |
| DD Documents | Design description | 2 | Hard & soft copy |
|  | Floor plan, elevation, section and site plan | 2 | Hard copy with A1 or A2 & soft copy |
|  | Specification and structural calculation (If needed) | 2 | Hard & soft copy |
|  | Approximate construction cost statement per DD dwg. | 2 | Hard & soft copy |
|  | All documents should be submitted as hard and soft copy. Soft copy can be delivered via USB and e-mail. All deliverables under this contract must be submitted in English and Russian versions. Bilingual format (English and Russian) may be used if needed. |  |  |

(c) Submittal List for the Construction Document (CD) Phase

| Submittal | Contents | 80% Copy | 100% Copy | Note |
| --- | --- | --- | --- | --- |
| Report for the termination of design | Design description | 2 | 4 | Hard & soft copy |
|  | Designers & engineers’ list and their signs |  |  |  |
|  | List of the submittal |  |  |  |
| Construction Document(CD) Drawings | Master layout plan, Floor plan, elevation, section, and details, etc. | 2 | 4 | Hard copy with A1 or A2 Designers and engineers’ sign should be added on the drawings |
|  | Site plan, civil engineering and landscape drawing |  |  |  |
|  | Electrical, communicational and fire protection drawing. |  |  |  |
|  | Aero view | - | 2 | Size 60cm x 120cm |
| Specification | General and special specification | 2 | 4 | Hard & soft copy |
| Structural Calculation | Structural calculation by structural engineer | 2 | 4 |  |
| Load Calculation | Mechanical, electrical, communicational and fire protection calculation | 2 | 4 |  |
| Construction Cost Statement for each Work Phase | Cost breakdown for the expected construction cost | 2 | 4 |  |
|  | Basis documents for cost estimation including quantity estimation |  |  |  |
| Licensing document (If needed) |  | 2 | 2 | Hard & soft copy |
| All documents should be submitted as hard and soft copy. Soft copy can be delivered via USB and e-mail. All deliverables under this contract must be submitted in English and Russian versions. Bilingual format (English and Russian) may be used if needed. * Both CAD format (or any original type) and copy of pdf format should be submitted for design document. * The fonts used in the drawings should be also delivered. * The construction cost estimation should be submitted in an excel file. |  |  |  |  |

D.  Design

(a)  The Buildings should be constructed to perform its given function reasonably by design.

(b)  Develop in response to the project site conditions and its functions, optimizing project site (land or building) use efficiency and accommodating future expansion (if required).

(c)  Eco-friendly and Barrier-free design

(d)  The Buildings shall be harmonized with existing buildings and surrounding circumstance.

(e)  Symbolic expression of Korea-Kyrgyzstan friendship

E.  Safety

(a)  Full consideration for means of evacuation, fire-resistant construction, and fire-car’s accessibility

(b)  Safe structure against earthquake

F.  Cost-Effective Design

(a)  Life Cycle Cost Efficiency

(b)  Indoor Comfort

(c)  Harmonize with structure, function, and sense of authenticity

(d)  Optimized circulation and space organization

G.  Others

(a)  Sustainable design through the application of appropriate materials and consideration of long-term maintenance.

(b)  Modernized design in alignment with the educational curriculum.

2.2.2. Considerations for Each Discipline

A.  Architectural Plan

(a)  Layout

i)  Plan in consideration of the aims of the Project

ii)  Layout in consideration of the project site access & boundary, infra lead-in conditions, site level, azimuth, existing plants, and other conditions

iii)  Optimum layout plan for the purpose of the project analyzing surroundings and circumstances

iv)  Efficient project site (land or building) use and future expansion (or for other use, if required)

(b)  Circulation

i)  Separate pedestrian circulation from vehicles

ii)  Emergency (and service) vehicle’s access

(c)  Plan

i)  Rational space program (adjustment if required) by each functional zone

ii)  Efficient module to eliminate wasted space

iii)  Minimize noise for indoor comfort, divide quiet space from noisy space and place an absorbing space in the middle.

iv)  Cost effective facility

(d)  Elevation

i)  Design making the most of Buildings’ characteristic in consideration of structural and formative aesthetics and material characteristics

ii)  Design in consideration of beauty and also its dignity as well as harmony with surroundings, getting high name-recognition

(e)  Section

i)  Decision of optimum story height by use, area, and characteristics of room to be an economic space program

ii)  Horizontal and vertical circulation plan for organic relation between operation and management while each function remains independent through zoning

B.  Structural Plan

(a)  Reinforced concrete should be used for the major structural frame work.

(b)  Detailed structural design for each part in consideration of standard of structural material, design strength, and conditions of load

(c)  Structural design including seismic design should meet the requirements of related laws and regulations.

(d)  Appropriate footing structure of the building in accordance with the soil survey result.

C.  MEP (Mechanical, Electrical, and Plumbing) Plan

(a)  Use highly efficient and energy-saving facility equipment and apparatus regarding cost-saving operation.

(b)  Facilities requiring frequent ventilation such as a toilet should be exposed directly to open air and equipped with both an active and passive ventilating system able to operate at the same time to prevent filthy from spreading out, and arrangement of storage for cleaning and sanitary supplies should be considered.

(c)  Ventilating system to allow the entrance of enough open air through a natural draft in the daytime, and in the time of passive ventilation, prevent inflow of outside noise, exhaust gas, dust, etc., paying attention to the window design.

(d)  Use a type of water-supply system through discussion with the Employer (or Recipient country) considering site situation, complying with local regulation, and a water tank considering sources of water-supply.

(e)  Electrical system should be able to reduce Life Cycle Cost and satisfy total economic efficiency through its reasonable use and the minimal loss of energy.

(f)  The electric power distribution system should minimize damage area from blackouts or any other incidents. The server and communication line should have anti-power failure system to secure reliability. This system should be planned for possible expansion as well.

(g)  Install a power generator (emergency stand-by generator) and UPS (w/AVR) to secure a stable power supply in case of emergency covering for laboratory’s equipment in the Buildings according to the consultation with the Employer (KOICA CM, PMC, etc.).

(h)  Install MCC for the centralized control of power-loads for each machine, and minimize the distance of each divergence circuit for current stability.

(i)  Electrical lighting system should be in harmony with natural light to maintain comfortable environment, and the installation of security lights outside should be considered.

(j)  Secure indoor comfort using dazzle-free light fixtures to relieve physiological and psychological stress.

(k)  Include internal and external broadcasting system, A/V system, streetlights in MEP design.

(l)  Establish an optimized telecommunication line for functions of the facility, and place power and network equipment in adequate spaces such as under the floor, inside the wall, etc. considering average consumption of users.

(m) Lightning protection equipment should meet the requirements of relative laws and regulations.

(n)  All the CCTVs and ancillary works for project site shall be installed to meet the requirements of relative laws and regulations and KOICA rules.

(n)  Place outlets adequately for convenient use of fixed and movable electric devices, and use moisture-proof outlets for humid space.

D.  Fire Protection Plan

(a)  Fire protection system shall be met with local law and regulation.

E.  Civil Plan

(a)  Civil plan should be done in connection with the building and other facilities by thorough analysis and investigation of the construction site along with geotechnical surveys about conditions of topography, soil, solid foundation, water level, etc., and required quantities and expenses should be estimated in the minimum value through a civil engineer’s professional reviews in economical and stability concerns

(b)  A civil engineer shall review stability through investigation not to generate any damage to buildings nearby due to civil construction, and the proper measures checked by a professional should be reflected in the design.

F.  Environment

(a)  Establish green-network linking neighbor forestry ecology, and consider ecological path closely connected with the public garden around nearby.

(b)  Use highly water permeable material to pave the pedestrian road, and maximize permeability to pave the road and parking lot.

G.  Others

- The site levelling plan, including access road, a rainwater management plan, should be applied to the design.

- The site surveying report and the public electricity and water service map shall be provided by Designer. For soil investigation report, min. 4 Bore Holes for the new construction buildings are required.

- Flag poles and Memorial stone are required in front of the building.

- All the signs for project site including  building sign in front of each building,  outdoor sign every zone,  sign panel or copper plate on the main gate or main entrance respectively, completion stone.

- All the signs every office/room/dormitory/function area inside building shall be installed.

- Network system for communication shall be provided.

- Stone Monument at site shall be installed.

- Pavements and curves, lower beds, shelter shall be provided.

- A septic tank, rainwater drainage system, wastewater disposal system shall be installed.

- The Consultant shall submit soil survey report to the Construction Manager (or through the Engineer) before starting the structural design and the substructure work of the building.

- Provide sidewalks and pedestrian ways paved with concrete bricks.

Article 3.  Description of Author’s Supervision Service

The supervision duties encompass the following responsibilities to ensure that the construction adheres to the intended design, technical standards, and project requirements:

  - Design Compliance Supervision

(a) Ensure that the construction is carried out in strict accordance with the approved design drawings, specifications, and technical standards.

(b) Review and approve any design modifications or adjustments required due to site conditions or unforeseen circumstances.

3-2. Material and Construction Quality Control

(a) Verify that the materials used in construction comply with the specified requirements and quality standards.

(b) Inspect construction methods and workmanship to ensure alignment with the design intent and industry best practices.

3-3. Coordination and Technical Support

(a) Provide technical guidance and clarification to the construction team regarding design-related issues.

(b) Collaborate with the project stakeholders, including contractors, engineers, and clients, to resolve any discrepancies between the design and actual site conditions.

3-4. Site Inspections and Progress Monitoring

(a) Should stay at site for necessary period for the construction, in order to monitor construction progress and inspect & assess compliance with the design specifications.

(b) Document findings, recommend corrective actions if necessary, and report to relevant parties.

  - Approval of Design-Related Changes

(a) Evaluate and approve any proposed design changes, ensuring they align with the overall project objectives and quality standards.

(b) Assess the impact of modifications on structural integrity, functionality, sustainability, and cost-effectiveness.

3-6. Final Inspection and Handover

(a) Conduct (as per the instruction from KOICA(CM) final inspections to verify that the completed structure aligns with the original design intent.

(b) Assist in the handover process, ensuring that all design-related documentation and as-built drawings are accurately completed.

This scope of work ensures that the integrity of the original design is maintained throughout the construction process while addressing any necessary adaptations or refinements.

The Service should include Author’s Supervision Scope of services according to the local law and the appropriate number of staff should be assigned and allocated for the supervision across all disciplines during the construction period.

If the construction period is extended, the author’s supervision period shall be extended accordingly, and the Consultant shall not be entitled to claim any increase in the contract price.

The Service include but not limited to the technical review on the priced detailed BoQ proposed by a successful bidder for the construction contract as a part of the bidding support for selecting the construction contractor.

<End>