Special Conditions of Contract

- Purpose

SCC shall supplement GCC with the specific provisions in GCC referred to and amended accordingly. The SCC provisions shall prevail over those in GCC and constitute a part of this Agreement.

- Contract Period and Consulting Period

- The Contract Period as defined in Section 1(g) of GCC shall be from the Effective Date to mm dd, 20yy. ( for 24months)

- The Consulting (for the design service) Period as defined in Section 1(h) of GCC shall be from the Effective Date to mm dd, 20yy. (for 9months)

ㅇProject Title:

The Design and Author Supervision Services for the Construction of ICT Education Center for “The Project for Capacity Building of National Information for Digital Transformation in the Kyrgyz Republic” in Bishkek, the Kyrgyz Republic

ㅇProject Timeline:

| Consulting Items | Period | Remarks |
| --- | --- | --- |
| Design | 9 months | Including relevant local authority’s permit |
| Bidding support & Author’s Supervision | 15 months | Tentative, Subject to change |
| Total | 24 months |  |

ㅇDesign period: for 9months in total

- delay damage deadline for the design service of the Contract.

ㅇBidding Support & Author’s Supervision period: 15 months(subject to change) during entire construction period till the official occupation of the buildings.

  - If the construction period is extended, the author’s supervision period shall be extended accordingly, and the Consultant shall not be entitled to claim any increase in the contract price.

  - Liquidated Damages(L.D.):

ㅇ 0.125% of the Contract price of Design service per day

ㅇ The L.D. shall be applied from the day after the end of Design period.

ㅇ The maximum L.D is 30% of the Contract price.

- Commencement of Project

The Consultant shall commence the Project within 10 days from the Effective Date; provided, however, that, in case that its delay is apparently expected in unavoidable circumstances, the Consultant shall obtain the approval of the Employer in advance.

- Payment of Project Expenses

- The Consultant shall demand the Project expenses based upon the implementation plan of the Contract Price, and the Employer shall pay such amount in U.S. dollar to the Consultant in its bank account [Name of the Bank and A/C Number, Owner's Name] within 14 days from the Consultant's demand:

- The Consultant may demand in advance the expenses necessary to prepare for the Project, and the Employer may pay such expenses after examination thereof.

- The Consultant may request the transfer of budget by item within the scope of the Contract Price so as to facilitate the execution of the Project, and the Employer may approve or reject such request after examination thereof.

- The Consultant shall apply for the Project expenses with the previous quarter performance report attached thereto in accordance with the implementation plan.

- The Employer may make payment in advance in accordance with the KOICA's Criteria on Advance Payment so as to facilitate the execution of the Project; provided, however, in such a case, that the submission of advance payment-related guarantee bond is required.

- Payment Conditions

| Payment at Phase | Amount | Remarks |
| --- | --- | --- |
| Advance Payment (A.P.) | Up to 30% of the design price at the maximum | A.P. bond should be presented with the payment request |
| 1st interim payment | 20% of the design price at the max. | Upon approval on the SD design document. |
| 2nd interim payment | 30% of the design price at the max. | Upon approval on the DD design document. |
| 3rd interim payment | 50% of the design price at the max. | Upon approval on both final CD document & the Bid document. |
| 4th interim payment | 30% of the author’s supervision price at the max. | Upon approval on the 50% progress completion of the new construction buildings. |
| 5th final payment | 70% of the author’s supervision price | Upon approval on the final report after the occupation permit of the new buildings. |

- Application of Exchange Rate

When the U.S. dollar is used for the purpose of payment under this Agreement, the exchange rate of T/T offered rate quoted on the 15th day of each month by the bank with which the Employer trades shall apply thereto.

- Post-Qualification Monitoring

- In performing the Consultant Services, the Consultant shall implement the content as specified in the Pre-Qualification Criteria thoroughly as promised by it during the initial qualification examination.

- The Employer shall monitor from time to time the performance of the Consultant as stated in Section 8.1, and, if any difference from the initial plan occurs, shall take measures to correct immediately such difference.

- Insurance and Casualty Compensation

- The Consultant shall upon the demand of the Employer, prior to the dispatch of personnel or, as the case may be, prior to the commencement of the Project, submit to the Employer a copy of insurance certificate issued on the occasion of insurance contract.

- The Consultant shall make the personnel, who are assigned to perform this Agreement, insured by the following criteria:

- In case of injury and death, up to maximum as per the local regulation & law;

- In case of disease and death, up to maximum as per the local regulation & law; or

- In case of special expenses, up to maximum as per the local regulation & law.

- Use of Patent

The Consultant shall be solely responsible for the use of the patent or other intellectual property rights of a third party in performing the Consultant Services; provided, however, that, the Employer, who has requested the execution or application of the Consultant Services without designating the method of performance thereof in the Agreement, may provide or arrange every kind of convenience, or expenses incurred therewith.

- Undertaking of Non-Bribery and Integrity Obligation

The Consultant shall consent to observe the undertaking, in which the Consultant shall not, on the basis of mutual trust with the Employer, engage unfair trade practices including prior concerted quotations in the course of bidding and being awarded, conclusion and performance of the contract, nor provide KOICA's officers and employees, and competent government officials with unjust compensation including bribery, entertaining treat, etc., and further that, in case of breach of such undertaking, it will accept and observe sanctions including the early termination of the Agreement.

- Language

The language of the Contract is English.

- Scope of Work

  - The Consultant should perform the Design & Engineering services, and Author’s Supervision service required from the local laws and the work scope specified in the Bid document [Section 5] Scope of Services.

  - The Consultant should provide conceptual layout options (3 options at the minimum) considering his/her project site survey result and design specifications per each option for the Employer to choose and approve the best option among the proposed options. And after the Employer’s official approval on the layout options, the Consultant should proceed to the next Schematic Design stage as per the RFP. This review and approval process should be included in the Design timeline and there will be no time extension due to this procedure

- Settlement of Accounts of Project Expenditure

| Service Items | Contract Price (USD) | Remarks |
| --- | --- | --- |
| Design Service | 11,163 |  |
| Author’s Supervision (Including Bidding support) | 99,600 |  |
| Total | 110,763 | VAT excluded |

※This Contract is Lumpsum price contract.

- Governing Law: Kyrgyzstan Law

- VAT

The Employer shall provide the required documents for the tax exemption. However, the Employer has no responsibility for tax exemption or refund since the State Customs Service and the State Tax Service under the Cabinet of Ministers of the Kyrgyz Republic as well as the Ministry of Digital Development and Innovative Technologies of the Kyrgyz Republic are responsible for tax collection and refund in accordance with the laws of the Kyrgyz Republic. <End>